

Fyfield Parish Council Clerk’s Report


5th October 2026
	Meeting Date
	Item No.
	Description
	Action/Decision
	Completed

	05.08.24
07.07.55
	24.52
25.45a
	Risk Register – points to be actioned
1. Fireproof storage
	Chubbsafe Archive Cabinet 880 XL (75 lever arch files) £2,378.74 inc delivery.
7-10 working days for delivery. Ready to go ahead.
	 

	05.08.24
07.07.25
	24.56
25.45b
	Viability of the telephone box
	Items to create the information station have been collated and added to the agenda to agree.
	

	06.10.25
	25.92b
	Land behind Walker Avenue – cancel lease
	Still waiting to hear from EFDC. Chased 16/9.
	

	06.07.26
	26.42
	Move from Xero to Scribe
	Ongoing.
	

	03.08.26
	26.58c
	Churchyard bin emptying
	I was put in touch with the wrong team so I have contacted the correct team and I’m waiting for a response (takes 10 working days).
	

	03.08.26
	26.60
	In-house councillor training
	Looking at dates in November and December. 
	

	14.09.26
	26.68a
	MoP concern for overgrown verge – contact Highways
	Emailed Essex Highways. Awaiting a response.
	

	14.09.26
	26.68b
	Village gateways move to correct position – contact Highways
	Resent our original email sent to Cllr J McIvor on 20th June 2025 (which was never responded to) to Essex Highways and ECC. Awaiting response.
	

	14.09.26
	26.72b
	Sovereign to treat the drill holes in the play area climbing frame
	Completed.
	23.09.2026

	14.09.26
	26.72d
	Confirm updated sports field maintenance schedule
	Completed.
	16.09.2026

	14.09.26
	26.72f
	Fix wobbly fence between VH car park and back of Walker Avenue
	Awaiting one quote and further contacts for another contractor.
	

	14.09.26
	26.73c
	Update the burial ground regulations regarding confetti
	I am going to liaise with Cllr L Webster to complete this.
	

	14.09.26
	26.74
	Join the Civility and Respect Pledge
	Completed.
	16.09.2026

	14.09.26
	26.76
	Charitable donation under Section 137
	Payment raised for authorisation.
	28.09.2026

	02.03.26
	25.162b
	Arrange pollarding of trees at front of St Nicholas 
	Emailed contractor. Awaiting reply.
	



